## Sprint1
Feature | User Story | Story Type | Story Point Value | Team Members | Work Completed
Add navigation Icons | As a mobile user, I want the navigation bar to have easily understood icons so that I can intuitively understand what each button represents | N | 3 | Jacob Morin | 15.7% (3 pt)
Add basic hydration tracking | As someone who has a history of being dehydrated, I want to be able to compare my water intake to the intake amount which would be considered in a healthy range so that I am not dehydrated less often. | F | 7 | Kyle Walker | 15.7% (3 pt)
Add basic nutrition tracking | As an overweight individual, I want to be able to set calorie goals each day to help keep myself from eating too much | F | 9 | Isaac Sparks-Willey | 21% (4 pt)
|  |  |  | Scott Audet | 15.7% (3 pt)
|  |  |  | Noi Knowles | 15.7% (3 pt)
|  |  |  | Ryan Handlon | 15.7% (3 pt)