## Sprint2
Feature | User Story | Story Type | Story Point Value | Done By: | Team Members | Velocity Points | Percentage
Onboarding launch display | As a new user, I want to enter my personal biometrics into my profile when I first open the app so that I don't have to re-enter it again unless my weight changes. | F - T | 5 | Scott | Jacob Morin | 3 | 17.65%
Food Mood | As someone who is a moody person, I would like to track my mood when I am eating so that I can learn about how the foods I eat correlate with my moods. | F - T | 3 | Kyle | Kyle Walker | 3 | 17.65%
Time stamp solution | As someone who is easily impressed by colorful graphs, I would like to be able to view my hydration as a graph on the home screen so that I feel more satisfied with using the app. | F- KA | 3 | Noi & Ryan | Isaac Sparks-Willey | 3 | 17.65%
Graph display | As a long term user, I want to create and view custom reports of past weeks so that I can compare nutrition progress. | F - T | 3 | Jacob | Scott Audet | 5 | 29.41%
Hydration mood planning | As someone who is a moody person, I would like to be able to see how each day’s hydration affects my mood so that I can learn about how much my hydration is affecting me. | F - KA | 3 | Isaac | Noi Knowles | 3 | 17.65%
[5 empty] | Ryan Handlon | 3 | 17.65%
|  | Sprint Velocity | 17